## Guide
Migration Checklist
Version 1.0 · FREE resource · Published by dataintelligenceinsights.com
WHAT IT IS | An execution checklist for moving data, pipelines and consumers from one data platform to another. It covers 43 checks across five phases — readiness, build and rehearsal, cutover, validation and reconciliation, and hypercare and decommission — and tracks progress, blocked and overdue work, and go/no-go gate readiness.
WHO IT IS FOR | Platform leads and engineers running a data platform migration (for example on-premises warehouse to cloud, or between cloud platforms), and the cutover manager who coordinates go/no-go.
HOW TO USE IT | 1. On the Checklist sheet, complete the migration details (name, source and target platforms, planned cutover date, go/no-go authority).
2. For each check, assign an owner and due date, then keep Status current: Not started, In progress, Done, Blocked or N/A. Record evidence (a link or reference) for every Done item.
3. Mark a check N/A only where it genuinely does not apply; N/A items are excluded from completion percentages.
4. Review the Summary sheet before each checkpoint and before the go/no-go meeting. Add rows for migration-specific checks by inserting them inside the table and copying the Flag formula down.
WHAT YOU PROVIDE | Owners, due dates, status and evidence for each check. Gate designations are pre-set for the checks that should block a go decision; you may change a check's Gate value if your governance differs.
WHAT THE OUTPUTS MEAN | Completion % = Done ÷ applicable checks (all checks not marked N/A). Blank status counts as Not started — it is never treated as complete.
Cutover readiness looks only at gate checks in phases 1 and 2. It reads READY only when every one of those gate checks is Done or N/A. It is an input to — not a substitute for — the go/no-go decision by the named authority.
Go-live acceptance looks at gate checks in phase 4 in the same way.
Flags: BLOCKED (status Blocked), OVERDUE (due date passed and not Done/N/A), Gate open (gate check not yet Done/N/A).
WORKED EXAMPLE | [EXAMPLE] Check MC-30 'Reconcile row counts per object…' — Owner: Data Engineering Lead · Due: cutover day +1 · Status: Done · Evidence: 'Recon report v3 — 214 of 214 tables within 0% tolerance; signed off by finance data owner.' (Fictional illustration; the Checklist itself ships blank.)
WORKBOOK MAP
Checklist | The working checklist: migration details, every check with owner, due date, status, evidence and an automatic flag.
Summary | Progress by phase, gate readiness for cutover and go-live, and the items needing attention.
Lists | Drop-down values used for validation.
CELL LEGEND
Sample | Input — enter or select your own information here.
Sample | Calculated — driven by formulas; do not overtype.
Sample | [EXAMPLE] Worked example — fictional illustration only. Delete or overwrite before use, or exclude via the summary toggle where provided.
LICENCE | This resource is provided under the dataintelligenceinsights.com Standard Use Licence v1.0. © dataintelligenceinsights.com. All rights reserved.
The full licence terms are set out in the dataintelligenceinsights.com Standard Use Licence v1.0.

## Checklist
Migration Checklist
Keep Status current for every check. Blue-tinted cells are inputs; grey cells are calculated.
| Migration name |  |  |  | Planned cutover date
| Source platform |  |  |  | Go/no-go authority
| Target platform |  |  |  | Last updated
ID | Phase | Check | Acceptance criterion (what 'done' looks like) | Gate | Owner | Due date | Status | Evidence / notes | Flag | Seq
MC-01 | 1. Readiness & planning | Confirm migration scope: in-scope datasets, pipelines, reports, integrations and user groups inventoried. | Scope inventory baselined and signed off by the migration sponsor. | Gate |  |  |  |  | Gate open
MC-02 | 1. Readiness & planning | Agree the migration approach (big-bang, phased by domain, or parallel run) and record the rationale. | Approach, sequencing and rationale approved. | Gate |  |  |  |  | Gate open
MC-03 | 1. Readiness & planning | Complete source-to-target mapping for every in-scope object (schemas, tables, data types, naming). | Mapping covers 100% of scope inventory; unmapped objects have a recorded decision. | Gate |  |  |  |  | Gate open
MC-04 | 1. Readiness & planning | Identify platform incompatibilities: SQL dialect, procedures/UDFs, collation, time zones, numeric precision, file formats. | Incompatibility log exists with a resolution or workaround per item. | —
MC-05 | 1. Readiness & planning | Map dependencies: upstream feeds, downstream consumers, schedules, service accounts and credentials. | Dependency list reviewed with each upstream and downstream owner. | —
MC-06 | 1. Readiness & planning | Design the target security model: roles, access policies, row/column-level controls, equivalent to source entitlements. | Security design approved by the data owner and information security. | Gate |  |  |  |  | Gate open
MC-07 | 1. Readiness & planning | Confirm sensitive-data handling on the target: classification, masking/encryption, data residency; privacy review where required. | Handling confirmed in writing; privacy review complete or recorded as not required. | Gate |  |  |  |  | Gate open
MC-08 | 1. Readiness & planning | Provision target environments (non-production and production); verify network connectivity and firewall rules. | Connectivity tested from every source and consumer location. | —
MC-09 | 1. Readiness & planning | Validate target capacity and cost estimate (compute sizing, storage, data egress) against expected volumes. | Estimate reviewed and within approved budget. | —
MC-10 | 1. Readiness & planning | Define the reconciliation approach: row counts, checksums or aggregate totals, key business measures and tolerance per object. | Reconciliation specification agreed with data owners before any production load. | Gate |  |  |  |  | Gate open
MC-11 | 1. Readiness & planning | Document the rollback plan: triggers, decision owner, steps, maximum rollback window, data re-sync method. | Rollback plan approved and rehearsed (see 2. Build & rehearsal). | Gate |  |  |  |  | Gate open
MC-12 | 1. Readiness & planning | Agree the communication plan: stakeholder notifications, change-freeze windows, user cut-over instructions. | Communication schedule issued to all affected groups. | —
MC-13 | 1. Readiness & planning | Name cutover roles, including a single go/no-go decision authority and escalation route. | Named roles confirmed; go/no-go authority recorded on this sheet. | —
MC-14 | 2. Build & rehearsal | Build migration tooling and scripts under version control with repeatable execution. | Scripts reproducible from source control in a clean environment. | —
MC-15 | 2. Build & rehearsal | Test historical/bulk data load in non-production using representative volumes. | Load completes within the planned window; failures investigated. | —
MC-16 | 2. Build & rehearsal | Rebuild or re-point pipelines and scheduled jobs; test end to end on the target. | All in-scope pipelines produce expected outputs on the target. | —
MC-17 | 2. Build & rehearsal | Validate downstream reports, dashboards and extracts against source outputs. | Side-by-side comparison passed for each critical output. | —
MC-18 | 2. Build & rehearsal | Run performance tests for key queries and loads against agreed targets. | Agreed performance targets met or exceptions accepted by the owner. | —
MC-19 | 2. Build & rehearsal | Execute a full dress rehearsal (mock cutover), including a rollback rehearsal, recording actual timings. | Rehearsal completed; actual timings fit the cutover window. | Gate |  |  |  |  | Gate open
MC-20 | 2. Build & rehearsal | Resolve rehearsal defects or accept them with a documented workaround. | No open severity-1/2 defects without an accepted workaround. | Gate |  |  |  |  | Gate open
MC-21 | 2. Build & rehearsal | Finalise the cutover runbook: step sequence, timings, owners, checkpoints, communications. | Runbook version-controlled and walked through with all cutover roles. | Gate |  |  |  |  | Gate open
MC-22 | 2. Build & rehearsal | Agree data and change freeze with source system owners. | Freeze window confirmed in writing. | —
MC-23 | 3. Cutover execution | Hold the go/no-go meeting; record the decision, attendees and open risks accepted. | Decision recorded by the named go/no-go authority, informed by the Cutover readiness view on the Summary sheet. | —
MC-24 | 3. Cutover execution | Take pre-cutover backups/snapshots of the source and confirm they are restorable. | Restore test passed or snapshot verified. | —
MC-25 | 3. Cutover execution | Freeze source writes or switch on delta capture as specified in the runbook. | Freeze/delta capture confirmed by the source owner. | —
MC-26 | 3. Cutover execution | Execute the final or delta data load; capture job logs. | Load complete with no unexplained failures; logs retained. | —
MC-27 | 3. Cutover execution | Switch schedules and integrations to the target; disable (do not delete) legacy schedules. | Legacy schedules disabled; target schedules active. | —
MC-28 | 3. Cutover execution | Enable access on the target for users and service accounts. | Access enabled per approved security model. | —
MC-29 | 3. Cutover execution | Track runbook checkpoint timings against plan and monitor rollback trigger points. | Checkpoint log maintained throughout cutover. | —
MC-30 | 4. Validation & reconciliation | Reconcile row counts per object within the agreed tolerance. | All objects within tolerance or exceptions accepted by the data owner. | Gate |  |  |  |  | Gate open
MC-31 | 4. Validation & reconciliation | Reconcile checksums, hash totals or column aggregates for critical objects. | Critical objects reconcile exactly or within stated tolerance. | Gate |  |  |  |  | Gate open
MC-32 | 4. Validation & reconciliation | Reconcile key business measures (e.g. period totals, entity counts) and obtain data-owner sign-off. | Data owners have signed off each key measure. | Gate |  |  |  |  | Gate open
MC-33 | 4. Validation & reconciliation | Verify referential integrity and key uniqueness on the target. | No orphaned keys or duplicate primary keys outside accepted exceptions. | —
MC-34 | 4. Validation & reconciliation | Validate security: test entitlements by role; confirm no excess access. | Role-based access tests passed. | Gate |  |  |  |  | Gate open
MC-35 | 4. Validation & reconciliation | Smoke-test critical reports and downstream consumers on the target. | All critical consumers confirmed working by their owners. | Gate |  |  |  |  | Gate open
MC-36 | 4. Validation & reconciliation | Obtain business acceptance to declare the migration live. | Formal acceptance recorded. | Gate |  |  |  |  | Gate open
MC-37 | 5. Hypercare & decommission | Stand up hypercare: support rota, triage route and exit criteria. | Hypercare rota published; exit criteria agreed. | —
MC-38 | 5. Hypercare & decommission | Activate monitoring and alerting on the target (pipeline failures, data freshness, cost). | Alerts route to a named owner and have been test-fired. | —
MC-39 | 5. Hypercare & decommission | Log post-migration issues and track them to closure. | Issue log maintained; hypercare exit criteria met. | —
MC-40 | 5. Hypercare & decommission | Keep the source read-only for the agreed fallback/retention period. | Source access set to read-only; retention end date recorded. | —
MC-41 | 5. Hypercare & decommission | Update documentation: catalogue, lineage, runbooks, data dictionary, support guides. | Documentation reflects the target platform. | —
MC-42 | 5. Hypercare & decommission | Approve legacy decommissioning: archive/retain data per policy; release licences and infrastructure. | Decommission approved by the system owner and records owner. | —
MC-43 | 5. Hypercare & decommission | Run a lessons-learned review and record actions. | Review held; actions assigned. | —
Formulas:
Flag = IF([Check]="","",IF([Status]="Blocked","BLOCKED",IF(AND(ISNUMBER([Due date]),[Due date]<TODAY(),[Status]<>"Done",[Status]<>"N/A"),"OVERDUE",IF(AND([Gate]="Gate",[Status]<>"Done",[Status]<>"N/A"),"Gate open",""))))

## Summary
Migration Summary
Migration: (name not yet entered on Checklist)
PROGRESS BY PHASE
Phase | Checks | Applicable | Done | In progress | Blocked | Not started | Overdue | Completion %
1. Readiness & planning | 13 | 13 | 0 | 0 | 0 | 13 | 0 | 0%
2. Build & rehearsal | 9 | 9 | 0 | 0 | 0 | 9 | 0 | 0%
3. Cutover execution | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0%
4. Validation & reconciliation | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0%
5. Hypercare & decommission | 7 | 7 | 0 | 0 | 0 | 7 | 0 | 0%
All phases | 43 | 43 | 0 | 0 | 0 | 43 | 0 | 0%
GATE READINESS
Gate scope | Gate checks | Done / N/A | Open | Blocked | Readiness status
Cutover readiness (phases 1–2) | 10 | 0 | 10 | 0 | NOT STARTED — no gate check has a status yet
Go-live acceptance (phase 4) | 6 | 0 | 6 | 0 | NOT STARTED — no gate check has a status yet
ATTENTION LIST — blocked and overdue checks (first 15)
ID | Check |  |  |  | Owner | Due date | Status | Flag
No blocked or overdue checks.
Completion % excludes N/A checks. Blank status is counted as Not started. Readiness status summarises gate checks only and does not replace the go/no-go decision.

## Lists
Status | Gate | Phase
Not started | Gate | 1. Readiness & planning
In progress | — | 2. Build & rehearsal
Done |  | 3. Cutover execution
Blocked |  | 4. Validation & reconciliation
N/A |  | 5. Hypercare & decommission